## Sheet1
Updated Gantt Chart
Trimester Two | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Deadline
| 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-19
Technical Documentation | bar: 2019-01-14 to 2019-01-21
Implementation Documentation | bar: 2019-01-21 to 2019-01-28
Features & Mechanics | bar: 2019-02-04 to 2019-03-25
Iterative Testing | bar: 2019-02-04 to 2019-04-01
Refactoring & Improvements | bar: 2019-04-01
Asset Production | bar: 2019-04-01
Targeted Testing | bar: 2019-04-08 to 2019-04-15
Deployment/Submission | bar: 2019-04-15 to 2019-04-19
Previous Gantt Chart (Created in Trimester 1)
Trimester Two | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Foundation Implementation | bar: Week 2 to Week 3
Blockout Modeling | bar: Week 2 to Week 3
Features & Mechanics | bar: Week 4 to Week 8
Model Design | bar: Week 9 to Week 10
Refactoring & Improvements | bar: Week 11
Continuous Minor Testing | bar: Week 2 to Week 11
Targeted Testing | bar: Week 12
Deployment/Submission | bar: Week 13