## Gantt
Trimester One | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 13
| 12th. Sept | 19th. Sept | 26th. Sept | 3rd. Oct | 10th. Oct | 17th. Oct | 24th. Oct | 31st. Oct | 7th. Nov | 14th. Nov | 21st. Nov | 28th. Nov | 30th Nov. (DEADLINE)
Project Management | Week 2: Absent; Week 3: Absent
Proposed Plan | Week 2: Absent; Week 3: Absent
Games Design Document | Week 2: Absent; Week 3: Absent
Technical Design Document | Week 2: Absent; Week 3: Absent
Prototype Design | Week 2: Absent; Week 3: Absent
Individual Critical Appraisal | Week 2: Absent; Week 3: Absent
Presentation | Week 2: Absent; Week 3: Absent
Submission | Week 2: Absent; Week 3: Absent
Trimester Two | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Foundation Implementation | bar: Absent Week 2 to Absent Week 3
Blockout Modeling | bar: Absent Week 2 to Absent Week 3
Features & Mechanics | bar: Absent Week 4 to Absent Week 8
Model Design | bar: Absent Week 9 to Absent Week 10
Refactoring & Improvements | bar: Absent Week 11
Continuous Minor Testing | bar: Absent Week 2 to Absent Week 11
Targeted Testing | bar: Absent Week 12
Deployment/Submission | bar: Absent Week 13

## Checklist
Component |  | Started | Completed | Weighting
Proposed Plan |  | No | No | 5%
◘ | Team List | No | No
◘ | Responsibilities & Roles | No | No
◘ | Game Proposal (Overview, Summary) | No | No
◘ | IDE | No | No
◘ | Gantt Charts (Both Trimesters) | No | No
◘ | Risk Analysis | No | No
Project Management |  | No | No | 10%
◘ | Weekly Personal Log (Minutes) | No | No
◘ | Minutes of Supervisor Meetings | No | No
◘ | Version Control Evidence | No | No
Games Design Document |  | No | No | 25%
◘ | Outline | No | No
◘ | Theme | No | No
◘ | Genre | No | No
◘ | Story/Narrative | No | No
◘ | Graphics/Sketches | No | No
◘ | Market Research | No | No
◘ | Level Design | No | No
◘ | Audio Design | No | No
Technical Design Document |  | No | No | 20%
◘ | Technical Approach | No | No
◘ | Game Platform | No | No
◘ | Hardware/Software Used | No | No
◘ | Programming Language | No | No
◘ | Mechanics & Gameplay | No | No
◘ | Rules of Game | No | No
◘ | Development Environment (In-Depth) | No | No
◘ | UI Sketch (Menu & Game) | No | No
Prototype Design |  | No | No | 30%
◘ | Prototype Developed | No | No
◘ | Image & Video Capture | No | No
◘ | Live Demo | No | No
Critical Appraisal (At least 1 page) |  | No | No | 10%
◘ | Opinion of Project | No | No
◘ | Contribution Breakdown | No | No
◘ | Problems/Resolutions | No | No
◘ | Future Implementation | No | No